## Project Timeline
S-SYSTEM PROJECT TIMELINE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
| Brain Storming and Planning |  | Not Started |  | 2021-02-01 | 2021-02-15 | 15 |  | Not Started
| Subtask 1.1 |  | Not Started |  | 2021-02-12 | 2021-02-22 | 11 |  | In Progress
| Requirements and Feasibility analysis |  | Not Started |  | 2021-02-16 | 2021-02-27 | 12 |  | Complete
| Subtask 2.1 |  | Not Started |  | 2021-02-28 | 2021-03-02 | 3 |  | On Hold
| Design |  | Not Started |  | 2021-03-05 | 2021-03-31 | 27
| Development and Coding |  | Not Started |  | 2021-03-03 | 2021-04-15 | 44
| Integration and Testing |  | Not Started |  | 2021-03-15 | 2021-04-20 | 37 | Prototype should be tested and ready by 30th April, 2021
| Implémentation development |  | Not Started |  | 2021-03-03 | 2021-04-20 | 49
| Task 3.0 |  | Not Started |  | 2021-04-21 | 2021-04-30 | 10
| Operation and Maintenance |  | Not Started |  | 2021-04-22 | 2021-04-25 | 4
|  |  | Not Started |  | 2021-04-26 | 2021-04-30 | 5
|  |  | Not Started |  | 2021-05-01 | 2021-05-15 | 15
|  |  | Not Started |  | 2021-05-16 | 2021-05-30 | 15
|  |  | Not Started |  | 2024-02-10 | 2024-02-17 | 8
|  |  | Not Started |  | 2024-02-15 | 2024-02-17 | 3
|  |  | Not Started |  | 2024-02-15 | 2024-02-15 | 1
|  |  | Not Started |  | 2024-02-15 | 2024-02-16 | 2
|  |  | Not Started |  | 2024-02-16 | 2024-02-16 | 1
|  |  | Not Started |  | 2024-02-15 | 2024-02-17 | 3

## BLANK - Project Timeline
S-SYSTEM PROJECT TIMELINE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS KEY
| Database design |  | Not Started | HAFIZ MALIK | 2021-02-03 | 30/04/2021 | #VALUE! |  | Not Started
| Interface /graphics | Login/ Interface | [6 empty] | In Progress
| Programming | [7 empty] | Complete
| Access level | [7 empty] | On Hold
Dash Board Design
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*